## Weekly Progress Log
Sr. No. | Date | Task Assigned | Task Completion Status | Guide Signature
1 | 2024-10-07 | Literature survey on AI-based robotics & autonomous systems | Completed
2 |  | Study on existing SLAM methods (GMapping, RTAB-Map, Cartographer) | Completed
3 | 2024-10-14 | Research object detection algorithms using YOLO, MobileNet, and CNNs | Completed
4 |  | Setup simulation environment using ROS2 and Gazebo | Completed
5 | 2024-10-21 | Develop basic object detection node in ROS2 using Python & OpenCV | Completed
6 |  | Integrate LiDAR and IMU sensor data into simulation stack | Completed
7 | 2024-10-28 | Implement basic SLAM module using ROS2 Nav2 stack | Completed
8 |  | Develop multi-sensor fusion node (EKF) for localization | Completed
9 | 2024-11-04 | Train object detection model using COCO/ImageNet datasets | Completed
10 |  | Test detection algorithm inside Gazebo simulated environment | Completed
11 | 2024-11-11 | Evaluate detection accuracy; fine-tune model parameters | Completed
12 |  | Integrate object detection pipeline with robot SLAM | Completed
13 | 2024-11-18 | Evaluate localization drift and SLAM map consistency | Completed
14 |  | Implement PID controller for motion and wheel coordination | Completed
15 | 2024-11-25 | Simulate autonomous navigation using path planning algorithm | Completed
16 |  | Add obstacle avoidance using global costmap | Completed
17 | 2024-12-02 | Explore Reinforcement Learning methods for path optimization | Completed
18 |  | Integrate RL path planner and evaluate reward-based learning | Completed
19 | 2024-12-09 | Design and implement fail-safe modules for collision scenarios | Completed
20 |  | Perform end-to-end simulation test and verify module communication | Completed
21 | 2024-12-16 | Compare CNN and traditional object detection methods | Completed
22 |  | Update literature review with modern ROS2 and ML advancements | Completed
23 | 2024-12-23 | Optimize ROS2 multi-threaded node execution | Completed
24 |  | Implement telemetry, data logging & post-processing analytics | Completed
25 | 2024-12-30 | Benchmark SLAM accuracy on varying trajectories/maps | Completed
26 |  | Analyze accuracy/latency metrics and compare module performances | Completed
27 | 2025-01-06 | Design final indoor demo scenario and simulation setup | Completed
28 |  | Final integration, bug fixing and cleanup of ROS2 package | Completed
29 | 2025-01-13 | Finalize documentation, write project report, and prepare presentation | Completed
30 |  | Submit report, conduct final system demo, and complete evaluation | Completed
2025-01-20
2025-01-27
2025-02-03
2025-02-10
2025-02-17
2025-02-24
2025-03-03
2025-03-10
2025-03-17
2025-03-24
2025-03-31